## 10-13 Update
Name | Duration | Start | Finish | % complete | Bucket | Milestone | Labels | Priority
Sprint 19 | 34 days | 2022-09-23 | 2022-11-09 | 17% |  | No |  | Medium
Sprint 19 DEV | 10 days | 2022-09-26 | 2022-10-07 | 55% | In Progress | No |  | Medium
Item List | 10 days | 2022-09-23 | 2022-10-07 | 0% |  | No |  | Medium
54670 - Delegations: Update station dropdown list format when assigning a station to a delegated user | 0 days | 2022-10-07 | 2022-10-07 | 100% | Complete | Yes | Internally Created | Medium
54671 - Delegations: There are instances that only 1 email is generated when assigning 2 services to the user | 0 days | 2022-10-07 | 2022-10-07 | 100% | Complete | Yes | Internally Created | Medium
57926 - DPP - MUN - Response due date is incorrect | 0 days | 2022-10-07 | 2022-10-07 | 100% | Complete | Yes | Client Requested;EMERGENCY | Medium
57581 - OCA: MISSDIG - UAT Circle Tool not honoring min/max for shape size for project tickets | 0 days | 2022-10-07 | 2022-10-07 | 100% | Complete | Yes | Client Requested | Medium
57640 - OCA - MUN - Incorrect WLSD for Destroyed markings ticket | 0 days | 2022-10-07 | 2022-10-07 | 100% | Complete | Yes | Client Requested | Medium
56825 - OCA - Shared Tickets - QA testing | 0 days | 2022-10-07 | 2022-10-07 | 100% | Complete | Yes | Internally Created | Medium
57635 - OCA - MUN - Ticket history not showing for specific user | 0 days | 2022-10-07 | 2022-10-07 | 100% | Complete | Yes | Client Requested | Medium
[Sprint 19] 56654 - OneCall application slowness - Analyze and Optimize 8 of 8 - API Add Logout Function | 0 days | 2022-10-07 | 2022-10-07 | 100% | Complete | Yes | Internally Created | Medium
[Sprint 19] 57662 - OCA: MISSDIG - SubmitToPAC queue processing failure correction - CHILD - NextGen (1 of 4) | 0 days | 2022-10-07 | 2022-10-07 | 70% | In Progress | Yes | Internally Created | Medium
57652 - OneCallAccess - MISS DIG IQE Error [Npgsq Error performing query - invalid geometry] | 0 days | 2022-10-07 | 2022-10-07 | 25% | In Progress | Yes | Internally Created | Medium
[Sprint 20] 57925 - POSR - MUN - Members cannot post another response even before due date | 0 days | 2022-10-07 | 2022-10-07 | 35% | Moved to Next Sprint | Yes | Client Requested;EMERGENCY | Medium
[Sprint 20] 57663 - OCA: MISSDIG - SubmitToPAC queue processing failure correction - CHILD - NextGenAPI (2 of 4) | 0 days | 2022-10-07 | 2022-10-07 | 25% | Moved to Next Sprint | Yes | Internally Created | Medium
[Sprint 20] 57772 - POSR - MISS DIG - Issue posting a response after 10 day window | 0 days | 2022-09-23 | 2022-09-23 | 60% | Moved to Next Sprint | Yes | Client Requested;EMERGENCY | Medium
[Sprint 20] 57215 - Management Tools - Can't view or complete JOB NEW status | 0 days | 2022-10-07 | 2022-10-07 | 60% | Moved to Next Sprint | Yes | Client Requested | Medium
[Sprint 20] 55360 - DPP - MISSDIG - Include more Lookup Tables on DPP UI for MISSDIG to manage | 0 days | 2022-10-07 | 2022-10-07 | 25% | Moved to Next Sprint | Yes | Client Requested | Medium
[Sprint 20] 57646 - DPP - MUN - EYD and Summary reports show discrepancies | 0 days | 2022-10-07 | 2022-10-07 | 25% | Moved to Next Sprint | Yes | Client Requested | Medium
[Sprint 20] 54496 - OneCall Access - MISS DIG - "Configure" the Add and Remove member option for Internal users | 0 days | 2022-10-07 | 2022-10-07 | 0% | Moved to Next Sprint | Yes | Internally Created | Medium
Sprint 19 Release | 1 day | 2022-10-14 | 2022-10-14 | 0% | To Do | No |  | Medium
Internal Testing / Release to Preprod | 2 days | 2022-10-14 | 2022-10-17 | 0% | To Do | No |  | Medium
Sprint 19 Client Testing on PreProd | 3 days | 2022-10-18 | 2022-10-20 | 0% | To Do | No |  | Medium
Sprint 19 bugs reported | 1 day | 2022-10-20 | 2022-10-20 | 0% | To Do | No |  | Medium
Sprint 19 bugs fixed and released | 15 days | 2022-10-20 | 2022-11-09 | 0% | To Do | No |  | Medium
Sprint 19 Prod rollout |  |  |  | 0% | To Do | No |  | Medium
Name | Duration | Start | Finish | % complete | Bucket | Milestone | Labels | Priority
Sprint 20 | 33 days | 2022-10-10 | 2022-11-23 | 0% |  | No |  | Medium
Sprint 20 DEV Duration | 10 days | 2022-10-10 | 2022-10-21 | 0% | In Progress | No |  | Medium
Items List | 0 days | 2022-10-21 | 2022-10-21 | 0% |  | Yes |  | Medium
[Sprint 20] 57925 - POSR - MUN - Members cannot post another response even before due date | 0 days | 2022-10-21 | 2022-10-21 | 0% | In Progress | Yes |  | Medium
[Sprint 20] 57663 - OCA: MISSDIG - SubmitToPAC queue processing failure correction - CHILD - NextGenAPI (2 of 4) | 0 days | 2022-10-21 | 2022-10-21 | 0% | In Progress | Yes |  | Medium
[Sprint 20] 57772 - POSR - MISS DIG - Issue posting a response after 10 day window | 0 days | 2022-10-21 | 2022-10-21 | 0% | In Progress | Yes |  | Medium
[Sprint 20] 57215 - Management Tools - Can't view or complete JOB NEW status | 0 days | 2022-10-21 | 2022-10-21 | 0% | In Progress | Yes |  | Medium
[Sprint 20] 55360 - DPP - MISSDIG - Include more Lookup Tables on DPP UI for MISSDIG to manage | 0 days | 2022-10-21 | 2022-10-21 | 0% | In Progress | Yes |  | Medium
[Sprint 20] 57646 - DPP - MUN - EYD and Summary reports show discrepancies | 0 days | 2022-10-21 | 2022-10-21 | 0% | In Progress | Yes |  | Medium
[Sprint 20] 54496 - OneCall Access - MISS DIG - "Configure" the Add and Remove member option for Internal users | 0 days | 2022-10-21 | 2022-10-21 | 0% | In Progress | Yes |  | Medium
Sprint 20 Release | 1 day | 2022-10-28 | 2022-10-28 | 0% | To Do | No |  | Medium
Internal Testing / Release to Preprod | 2 days | 2022-10-28 | 2022-10-31 | 0% | To Do | No |  | Medium
Sprint 20 Client Testing on Preprod | 3 days | 2022-11-01 | 2022-11-03 | 0% | To Do | No |  | Medium
Sprint 20 bugs reported | 1 day | 2022-11-03 | 2022-11-03 | 0% | To Do | No |  | Medium
Spritn 20 bugs fixes and release | 15 days | 2022-11-03 | 2022-11-23 | 0% | To Do | No |  | Medium
WLSD Items Regarding the Date Compliance issues in the system, the Pelican Development Team has been working on the various issues related to Date Compliance for the last week and a half. All issues identified have been worked on and are in the QA/Testing phase. Pelican is currently running through some regression testing around these date issues. As of today, we have confirmed with the Pelican Development Team that testing on the majority of the issues is well underway and anticipate finalizied Pelican testing by the end of this week. (Yay!) Pelican is working with the QA team to look at releasing their tested work (assuming that testing passes) next week allowing the MISS DIG team to perform additional internal testing. We will be able to provide better dates on testing and releases next week.
SHARE FEATURE Currently, we do not have any further updates since last week other than they are finishing up outstanding development items for the Share Feature. The Demo of the share feature, which can be accessed from this dropbox folder Share Feature Demo, is still available for viewing only and not sharing. We are still hoping to have external testing open on 11/02/22, but more updates on that will be coming soon.
https://www.dropbox.com/scl/fo/ow9sldf6pb7lyz465fc0g/h?dl=0&rlkey=71mmmf8nn80d2box4fl5z7u5l

## 8-25 Update
Name | Duration | Start | Finish | % complete | Bucket | Depends on | Dependents (after) | Milestone | Labels
Sprint (14) | 35 days | 2022-07-18 | 2022-09-02 | 99% |  |  |  | No
Sprint 14 Dev | 10 days | 2022-07-18 | 2022-07-29 | 100% | Done |  | 17 - 55591 - QA Delegated user has more rights than his role, 5 - 56048 - Delegations Add Station code to Delegated Companies table, 6 - 57154 - The Station History is not always displayed, 59 - [Sprint 17] 57215 - Management Tools - Can't view or complete JOB NEW status, 4 - 55591 - DEV Delegated user has more rights than his role, 7 - 54646 - DPP - EYD export file name | No
Item List | 1 day | 2022-07-29 | 2022-07-29 | 100% |  |  |  | No
55591 - DEV Delegated user has more rights than his role | 0 days | 2022-07-29 | 2022-07-29 | 100% | Done | 2 - Sprint 14 Dev |  | Yes | Client Requested
56048 - Delegations Add Station code to Delegated Companies table | 0 days | 2022-07-29 | 2022-07-29 | 100% | Done | 2 - Sprint 14 Dev |  | Yes | Internally Created
57154 - The Station History is not always displayed | 0 days | 2022-07-29 | 2022-07-29 | 100% | Done | 2 - Sprint 14 Dev |  | Yes | Internally Created
54646 - DPP - EYD export file name | 0 days | 2022-07-29 | 2022-07-29 | 100% | Done | 2 - Sprint 14 Dev |  | Yes | Internally Created
Sprint Release (STAGING)) | 0 days | 2022-08-05 | 2022-08-05 | 100% | Done |  | 10 - Sprint Client Testing on PreProd | Yes
Internal Testing and move to Preprod | 2 days | 2022-08-08 | 2022-08-09 | 100% | Doing |  |  | No
Sprint Client Testing on PreProd | 2 days | 2022-08-10 | 2022-08-11 | 100% | Doing | 8 - Sprint Release (STAGING)) | 11 - Sprint bugs reported | No
Sprint bugs reported | 0 days | 2022-08-11 | 2022-08-11 | 100% | To Do | 10 - Sprint Client Testing on PreProd |  | Yes
Sprint bugs fixed and released | 15 days | 2022-08-15 | 2022-09-02 | 100% | To Do |  | 13 - Sprint Prod rollout | No
Sprint Prod rollout | 0 days | 2022-08-25 | 2022-08-25 | 0% | To Do | 12 - Sprint bugs fixed and released |  | Yes
Sprint (15) | 32 days | 2022-08-01 | 2022-09-13 | 43% |  |  |  | No
Sprint 15 Dev | 10 days | 2022-08-01 | 2022-08-12 | 100% | Done |  | 57 - [Sprint 17] 56654 - OneCall application slowness - Analyze and Optimize 8 of 8 - API Add Logout Function, 58 - [Sprint 17] 56049 - Bulk edit subscriptions/users and companies, 22 - 54644 - EDY Advanced Search changes, 21 - 57471 - MISSDIG - Force start date and time to be equal to calculated earliest possible start date time, 18 - 57449 - MISS DIG - Work to Begin & Work Legal Start Date and Times are transmitting incorrectly, 19 - 57472 - OCA - MUN - Member did not receive Ticket that covered their AOI, 56 - [Sprint 17] 57416 - OCA: MISSDIG - SubmitToPAC queue processing failure correction, 33 - [Sprint 16] 55188 - Google Analytics - POC | No
Item List | 1 day | 2022-08-12 | 2022-08-12 | 100% |  |  |  | No
55591 - QA Delegated user has more rights than his role | 0 days | 2022-08-12 | 2022-08-12 | 100% | Doing | 2 - Sprint 14 Dev |  | Yes | Client Requested
57449 - MISS DIG - Work to Begin & Work Legal Start Date and Times are transmitting incorrectly | 0 days | 2022-08-12 | 2022-08-12 | 100% | Doing | 15 - Sprint 15 Dev |  | Yes | Client Requested;EMERGENCY
57472 - OCA - MUN - Member did not receive Ticket that covered their AOI | 0 days | 2022-08-12 | 2022-08-12 | 100% | Doing | 15 - Sprint 15 Dev |  | Yes | Client Requested;EMERGENCY
56428 - Authority Viewer - Multiple Live Layers | 0 days | 2022-08-12 | 2022-08-12 | 100% | To Do |  |  | Yes | Client Requested
57471 - MISSDIG - Force start date and time to be equal to calculated earliest possible start date time | 0 days | 2022-08-12 | 2022-08-12 | 100% | Doing | 15 - Sprint 15 Dev |  | Yes | Internally Created
54644 - EDY Advanced Search changes | 0 days | 2022-08-12 | 2022-08-12 | 100% | Doing | 15 - Sprint 15 Dev |  | Yes | Internally Created
Sprint 15 Release to STAGING | 0 days | 2022-08-19 | 2022-08-19 | 100% | Done |  | 25 - Sprint 15 Client Testing on PreProd | Yes
Internal Testing / Release to Preprod | 3 days | 2022-08-19 | 2022-08-23 | 100% | Done |  |  | No
Sprint 15 Client Testing on PreProd | 2 days | 2022-08-23 | 2022-08-24 | 0% | Doing | 23 - Sprint 15 Release to STAGING | 26 - Sprint 15 bugs reported | No
Sprint 15 bugs reported | 0 days | 2022-08-24 | 2022-08-24 | 0% | To Do | 25 - Sprint 15 Client Testing on PreProd |  | Yes
Sprint 15 bugs fixed and released | 15 days | 2022-08-24 | 2022-09-13 | 0% | To Do |  | 28 - Sprint 15 Prod rollout | No
Sprint 15 Prod rollout | 0 days | 2022-08-25 | 2022-08-25 | 0% | To Do | 27 - Sprint 15 bugs fixed and released |  | Yes
Sprint 16 (8/15/22-8/26/22) Items will be ready for MISS DIG testing on 9/12/22 with the latest the push to Prod for these items would be 9/30/22, except the Share feature items.
Next Sprint (16) | 35 days | 2022-08-15 | 2022-09-30 | 17% |  |  |  | No
Sprint 16 Dev | 10 days | 2022-08-15 | 2022-08-26 | 53% | Doing |  |  | No
Item List | 0 days | 2022-08-25 | 2022-08-26 | 0% |  |  |  | Yes
[Sprint 16] 57470 - DPP: MISSDIG - Users lose access to delegations OFF and ON | 0 days | 2022-08-25 | 2022-08-25 | 0% | Doing |  |  | Yes | Client Requested
[Sprint 16] 55188 - Google Analytics - POC | 0 days | 2022-08-26 | 2022-08-26 | 60% | Doing | 15 - Sprint 15 Dev |  | Yes | Internally Created
56812 - OCA - Shared Tickets - OCA API - Add search/view/create/update onecall api endpoints for ShareLink | 0 days | 2022-08-26 | 2022-08-26 | 0% | Doing |  |  | Yes | Internally Created
56813 - OCA - Shared Tickets - OCA API - Send notification emails | 0 days | 2022-08-26 | 2022-08-26 | 0% | Doing |  |  | Yes | Internally Created
56814 - OCA - Shared Tickets - OCA API - History api changes | 0 days | 2022-08-26 | 2022-08-26 | 0% | Doing |  |  | Yes | Internally Created
56815 - OCA - Shared Tickets - OCA API - Submit enquiry api changes | 0 days | 2022-08-26 | 2022-08-26 | 0% | Doing |  |  | Yes | Internally Created
56816 - OCA - Shared Tickets - OCA API - Get enquiry api changes | 0 days | 2022-08-26 | 2022-08-26 | 0% | Doing |  |  | Yes | Internally Created
56817 - OCA - Shared Tickets - OneCallAccess - UI - Build new screen for Share Links | 0 days | 2022-08-26 | 2022-08-26 | 0% | Doing |  |  | Yes | Internally Created
56818 - OCA - Shared Tickets - OneCallAccess - Add Share Link create/update overlay (panel)- API integration | 0 days | 2022-08-26 | 2022-08-26 | 0% | Doing |  |  | Yes | Internally Created
56821 - OCA - Shared Tickets - OCA - View job summary page UI changes | 0 days | 2022-08-26 | 2022-08-26 | 0% | Doing |  |  | Yes | Internally Created
56822 - OCA - Shared Tickets - OCA - Register user UI changes | 0 days | 2022-08-26 | 2022-08-26 | 0% | Doing |  |  | Yes | Internally Created
56823 - OCA - Shared Tickets - OneCallAccess - Integration with API | 0 days | 2022-08-26 | 2022-08-26 | 0% | Doing |  |  | Yes | Internally Created
56851 - OCA - Shared Tickets - Review and Guidance | 0 days | 2022-08-26 | 2022-08-26 | 0% | Doing |  |  | Yes | Internally Created
57447 - DPP: MISSDIG - Lookup Table > Searching in Name of Authorities fails | 0 days | 2022-08-26 | 2022-08-26 | 30% | Doing |  |  | Yes | Internally Created
57453 - PAC/POSR queries for LegalStartDate compliance | 0 days | 2022-08-26 | 2022-08-26 | 30% | Doing |  |  | Yes | Internally Created
Sprint 16 Release | 0 days | 2022-09-02 | 2022-09-02 | 0% | To Do |  | 49 - Sprint 16 Client Testing on PreProd | Yes
Internal Testing / Release to Preprod | 2 days | 2022-09-02 | 2022-09-05 | 0% | To Do |  |  | No
Sprint 16 Client Testing on PreProd | 4 days | 2022-09-05 | 2022-09-08 | 0% | To Do | 47 - Sprint 16 Release | 50 - Sprint 16 bugs reported | No
Sprint 16 bugs reported | 0 days | 2022-09-08 | 2022-09-08 | 0% | To Do | 49 - Sprint 16 Client Testing on PreProd |  | Yes
Sprint 16 bugs fixed and released | 15 days | 2022-09-12 | 2022-09-30 | 0% | To Do |  | 52 - Sprint 16 Prod rollout | No
Sprint 16 Prod rollout | 0 days | 2022-09-30 | 2022-09-30 | 0% | To Do | 51 - Sprint 16 bugs fixed and released |  | Yes
Sprint 17 (8/29/22- 9/9/22) is being filled with roll over items as well as items from out outstanding list.
Future Sprint (17) | 40 days | 2022-08-29 | 2022-10-21 | 0% |  |  |  | No
Sprint 17 Dev | 10 days | 2022-08-29 | 2022-09-09 | 0% | To Do |  |  | No
Item List | 0 days | 2022-09-09 | 2022-09-09 | 0% |  |  |  | Yes
[Sprint 17] 57416 - OCA: MISSDIG - SubmitToPAC queue processing failure correction | 0 days | 2022-09-09 | 2022-09-09 | 40% | Doing | 15 - Sprint 15 Dev |  | Yes | Internally Created
[Sprint 17] 56654 - OneCall application slowness - Analyze and Optimize 8 of 8 - API Add Logout Function | 0 days | 2022-09-09 | 2022-09-09 | 40% | Doing | 15 - Sprint 15 Dev |  | Yes | Internally Created
[Sprint 17] 56049 - Bulk edit subscriptions/users and companies | 0 days | 2022-09-09 | 2022-09-09 | 15% | Doing | 15 - Sprint 15 Dev |  | Yes | Internally Created
[Sprint 17] 57215 - Management Tools - Can't view or complete JOB NEW status | 0 days | 2022-09-09 | 2022-09-09 | 60% | To Do | 2 - Sprint 14 Dev |  | Yes | Internally Created
Sprint 17 Release | 0 days | 2022-09-16 | 2022-09-16 | 0% | To Do |  |  | Yes
Internal Testing / Release to Preprod | 2 days | 2022-09-16 | 2022-09-19 | 0% | To Do |  |  | No
Sprint 17 Client Testing on PreProd | 4 days | 2022-09-19 | 2022-09-22 | 0% | To Do |  |  | No
Sprint 17 bugs reported | 0 days | 2022-09-22 | 2022-09-22 | 0% | To Do |  |  | Yes
Sprint 17 bugs fixed and released | 15 days | 2022-09-26 | 2022-10-14 | 0% | To Do |  |  | No
Sprint 17 Prod rollout | 1 day | 2022-10-21 | 2022-10-21 | 0% | To Do |  |  | No